## llm_README
llm_README - Workbook Documentation
WORKBOOK SUMMARY
Business Purpose: | Construction/Real Estate project budget management system. Tracks job setup, forecasts, budgets, vendor details, tenant estimates, and payment applications. Contains logging mechanisms for budget changes and error tracking.
Metrics:
- Total Sheets: | 11 (excluding llm_README)
- Visible Sheets: | 11
- Hidden Sheets: | 0
- Generation Mode: | standard
- Generated: | 2025-08-03T04:47:55.965Z
SHEET DETAILS
Sheet: 00_JobSetup
- Dimensions: | 37 rows x 18 columns
- Used Range: | B2:D31
- Headers: | Row 7: Vendor (B7), Category (C7), Forecasted Cost Type (D7)
Sheet: 01_ForecastLog
- Dimensions: | 66 rows x 6 columns
- Used Range: | B2:S38
═══════════════════════════════════════════
DETAILED SHEET ANALYSIS
═══════════════════════════════════════════
1. 00_JobSetup (Type: Setup)
Dimensions: |  | 37 rows × 18 columns
Used Range: |  | A1:D31
Purpose: |  | Initial job configuration with property details and vendor assignments
Headers Found: |  | A7:, B7:Vendor, C7:Category, D7:Forecasted Cost Type
2. 01_ForecastLog (Type: Log)
Dimensions: |  | 66 rows × 6 columns
Used Range: |  | A1:S38
Purpose: |  | Tracks forecast changes and budget modifications over time
Headers Found: |  | A7:, B7:Category, C7:Budget Type, D7:Budget Amount, E7:Budget Status, F7:Date Entered, G7:Budget Notes, H7:, I7:, J7:, K7:, L7:, M7:, N7:, O7:, P7:, Q7:, R7:, S7:
3. 02_BudgetLog (Type: Log)
Dimensions: |  | 62 rows × 12 columns
Used Range: |  | A1:G67
4-10. Additional Sheets Summary: |  | Detailed budget tracking log with categories and amounts
• 03_BudgetReport: |  | A7:, B7:Category, C7:Original Budget, D7:Approved Changes, E7:Revised Budget, F7:Revised Budget PSF, G7:Committed Cost | Consolidated budget reporting with actuals vs forecasts
• 04_VendorDetail: |  |  | Vendor information and contract details
• zz_data: |  |  | Master data table with property and vendor information
• ErrorLog: |  |  | System error tracking and debugging log
• zzz_yardi import: |  |  | Yardi system data import staging area
• TENANT_ESTIMATE: |  |  | Tenant improvement cost estimates
• PAY_APP: |  |  | Payment application processing
═══════════════════════════════════════════
GLOBAL ANALYSIS
═══════════════════════════════════════════
• 00_JobSetup → references tblProperties table (in 04_VendorDetail sheet)
• 00_JobSetup → references tblProperties table (likely in zz_data)
• BudgetLog/ForecastLog → feed into BudgetReport
• PAY_APP → processes vendor payments from VendorDetail
• zzz_yardi import → external data source integration
Identified Risks:
• [MEDIUM] INDEX/MATCH formulas without error handling
• [LOW] Multiple sheets with similar names (potential confusion)
• [MEDIUM] No apparent data validation on input fields
• [LOW] Inconsistent naming convention (mix of numbered/named sheets)
Recommendations:
1. Add IFERROR wrapper to INDEX/MATCH formulas
2. Implement data validation on key input fields
3. Create named ranges for frequently referenced cells
4. Consider prefixing sheets (INP_, CALC_, OUT_, CHK_)
5. Add error handling to external data imports
═══════════════════════════════════════════
Generated by llm_README v4.0 — 2025-08-02 — Optimizer ≥ 2.6, Agent ≥ 4.1
Structured Tables Found:
• 00_JobSetup: tblForecastLog (B7:H37)
• 01_ForecastLog: tblBudetLog (B7:G67)
• 02_BudgetLog: tblBudget (B7:M64)
• 04_VendorDetail: tblProperties (B1:C63)
• 04_VendorDetail: tblVendors (G1:H124)
• 04_VendorDetail: tblCostCodes (J1:L95)
• 04_VendorDetail: tblLookups (N1:T16)
• 04_VendorDetail: ProjectManagers (E1:E6)
Data Organization:
• Master data tables are centralized in 04_VendorDetail sheet
• Error logging tracked in ErrorLog sheet
• Budget workflow: ForecastLog → BudgetLog → BudgetReport
• External integration via zzz_yardi import sheet

## README_Instructions
RJK CONSTRUCTION - BUDGET TRACKER
Purpose:
This workbook is the new required standard for all budgeting, estimating, job tracking, and forecasting of any kind for construction projects at RJ Kelly.
Color Legend:
Cells in blue font are for manual input by Project Managers. All other cells are locked.
Cells in black font are formula's and are not able to be edited
Workflow:
Step 1: Job Setup: Navigate to '01_Job Setup' tab and fill in the project's high-level details and scope of work.
Step 2: Build Forecast & Budget: Use Commitment, Estimate, and Budget Logs to create Forecast and Budget amounts that populate in '05_Budget_Report'. Based on Cost Code Category and Vendor. -'02_Commitment_Log' : Record Subcontracts, Subcontract Change Orders, and Material Purchase Orders. Feeds into PM Forecast when 'Approved' status. -'03_PCC_Log' : Record Probably Construction Cost (PCC) estimates. Feeds into PM Forecast when 'Approved' status. -'04_Budget_Log' : Record Original Budget and any Budget changes. Feeds into Original and Revised Budget.
Step 3: Tracking and Updating Budget: Track & Forecast: As the job progresses: - Log all contracts and POs in the '03_Commitment_Log'. - Log all budget changes in the '04_Change_Order_Log'. - Regularly update the 'Invoiced Cost' and 'PM Forecasted Final Cost' columns on the '02_Budget_Forecast' sheet to maintain an accurate projection.
PROJECT COST MANAGEMENT WORKBOOK - COMPREHENSIVE README
Generated: 2025-07-20 00:29 UTC
OVERVIEW
This workbook is RJK Construction's standardized project cost management system for budget tracking, forecasting, and financial reporting of construction projects. It integrates job setup parameters, commitment logging, potential cost tracking, and budget management into a comprehensive dashboard that provides real-time budget vs. actual analysis with Power Pivot data model integration for historical invoice tracking.
WORKBOOK STRUCTURE
• Total Sheets: 11
• Structured Tables: 8 (tblCommitments, tblPotentialCosts, tblBudetLog, tblBudget, tblProperties, tblVendors, tblCostCodes, tblLookups, ProjectManagers)
• Power Pivot Data Model: Yes (ThisWorkbookDataModel with CUBE formulas)
• VBA Macros: None
• Charts: None currently
SHEET-BY-SHEET GUIDE
1. README_Instructions
• Purpose: Basic user instructions and color legend
• Key Info: Blue font = manual input by PMs, Black font = locked formulas
• Workflow: Job Setup → Build Forecast & Budget using logs
2. 01_Job_Setup (INPUT SHEET)
• Purpose: Project configuration and high-level parameters
• Key Fields: Property (12inno), Job Name (12Inno Bldg Demise), PM (Doug Malone), Status (BUDGETING), Type (CAPEX)
• Dependencies: Feeds project info to all other sheets via cell references
• User Action: Complete all blue font fields before proceeding to logs
3. 02_Commitment_Log (INPUT SHEET)
• Purpose: Record subcontracts, change orders, and purchase orders
• Table: tblCommitments (linked to Budget Forecast)
• Key Fields: Category, Vendor, Commitment Amount, Status
• Formula Logic: Only 'Approved' status commitments feed into forecast
4. 03_PCC_Log (INPUT SHEET)
• Purpose: Track Probable Construction Cost estimates
• Table: tblPotentialCosts (linked to Budget Forecast)
• Key Fields: Category, PCC Amount, Status
• Formula Logic: Only 'Approved' status PCCs feed into forecast
5. ErrorLog (SYSTEM SHEET)
• Purpose: Tracks system errors and validation issues
• Usage: Monitor for data integrity problems
6. 04_Budget_Log (INPUT SHEET)
• Purpose: Record original budgets and budget adjustments
• Table: tblBudetLog (feeds Budget Forecast)
• Key Fields: Category, Budget Type (Original Budget/Budget Adjustment), Budget Amount
7. 05_Budget_Forecast (OUTPUT DASHBOARD)
• Purpose: Main reporting dashboard with comprehensive budget analysis
• Table: tblBudget (calculated output table)
• Key Calculations:
- Revised Budget = Original Budget + Approved Changes
- Forecasted Final Cost = Committed Cost + PCC
- Forecasted (Over)/Under = Revised Budget - Forecasted Final Cost
• Advanced Features: Dynamic category list with LET formulas, CUBE formulas for historical data
8. zz_data (REFERENCE DATA)
• Purpose: Master data tables for lookups and validation
• Tables: tblProperties, tblVendors, tblCostCodes, tblLookups, ProjectManagers
• Largest dataset: 123 rows × 19 columns
9. zzz_yardi import (DATA IMPORT)
• Purpose: Staging area for Yardi system data imports
• Size: 27 rows × 6 columns
10. TENANT_ESTIMATE (CALCULATION SHEET)
• Purpose: Tenant-specific cost estimates and allocations
• Size: 25 rows × 4 columns
11. PAY_APP (PAYMENT APPLICATION)
• Purpose: Payment application processing and tracking
• Size: 49 rows × 31 columns
• Known Issues: Multiple #VALUE! errors in calculated columns V, Y, Z
DATA FLOW WORKFLOW
┌─────────────────┐ ┌──────────────────┐ ┌─────────────────┐
│ 01_Job_Setup │───▶│ Log Sheets │───▶│ 05_Budget_ │
│ (Parameters) │ │ • Commitment Log │ │ Forecast │
│ │ │ • PCC Log │ │ (Dashboard) │
│ │ │ • Budget Log │ │ │
└─────────────────┘ └──────────────────┘ └─────────────────┘
│ │ ▲
│ ┌────────▼────────┐ │
│ │ zz_data │ │
│ │ (Reference │ │
│ │ Tables) │ │
│ └─────────────────┘ │
│ │
▼ │
┌─────────────────┐ ┌─────────────────────────┘
│ Power Pivot │ │ CUBE Formulas
│ Data Model │◀─────────────┤ (Historical Data)
│ (Historical) │ │
└─────────────────┘ └
USER INSTRUCTIONS
STEP 1: Initial Project Setup
• Navigate to '01_Job_Setup' tab
• Complete all fields with blue font (manual input)
• Critical fields: Property code, Job name, Project Manager, Status, Type
• Ensure Yardi Job Code is accurate for system integration
STEP 2: Budget Entry
• Use '04_Budget_Log' to enter original budget amounts by category
• Budget Type options: 'Original Budget' or 'Budget Adjustment'
• Categories must match reference data in zz_data sheet
STEP 3: Commitment Tracking
• Record all subcontracts and purchase orders in '02_Commitment_Log'
• Set Status to 'Approved' only when commitment is finalized
• Link to vendors in tblVendors for consistency
STEP 4: Potential Cost Estimates
• Use '03_PCC_Log' for probable construction cost estimates
• Only set Status to 'Approved' for realistic estimates
• PCC amounts help project final costs before commitments
STEP 5: Monitor Dashboard
• Review '05_Budget_Forecast' for real-time budget analysis
• Key metrics: Forecasted (Over)/Under budget by category
• Monitor categories showing potential overruns
DATA REFRESH INSTRUCTIONS
• Budget Forecast updates automatically when log data changes
• Power Pivot refresh: Data > Refresh All (for historical CUBE data)
• Manual calculation: Ctrl+Alt+F9 (if calculation mode is manual)
KEY FORMULAS & TECHNICAL FEATURES
ADVANCED FORMULAS IN BUDGET FORECAST:
• Dynamic Category List (Column B):
LET formula combining table categories with Power Pivot members
- Aggregates categories from: tblPotentialCosts, tblCommitments, tblBudetLog
- Merges with CUBE data model categories using CUBESET/CUBERANKEDMEMBER
- Eliminates duplicates and sorts alphabetically
• Budget Calculations (Columns C-I):
- SUMIFS formulas linking to structured table references
- Status-dependent logic (only 'Approved' items included)
- Table references: [@Category] for dynamic row context
• Historical Data Integration (Column J):
- CUBEVALUE formulas accessing ThisWorkbookDataModel
- Measure: [Amount by _Category] for invoice history
- Dynamic member reference using CUBEMEMBER function
- IFNA error handling for missing categories
STRUCTURED TABLE RELATIONSHIPS:
• tblCommitments → Budget Forecast (Committed Cost column)
• tblPotentialCosts → Budget Forecast (PCC column)
• tblBudetLog → Budget Forecast (Original Budget & Approved Changes)
• tblProperties → Job Setup validation and display names
• Power Pivot Model → Historical invoice data via CUBE formulas
KNOWN ISSUES & RISK AREAS
IMMEDIATE ATTENTION REQUIRED:
• PAY_APP Sheet: Multiple #VALUE! errors in calculation columns V, Y, Z
- Affects payment application accuracy
- Requires formula review and correction
• CUBE Formula Errors: #NAME? errors in Budget Forecast Column J
- Power Pivot data model may need refresh
- Check Power Pivot connection and measures
PERFORMANCE CONSIDERATIONS:
• Complex LET formulas in Budget Forecast may slow recalculation
• CUBE formulas are volatile and recalculate frequently
• Large dataset in zz_data (123×19) affects lookup performance
• Consider manual calculation mode during heavy data entry
DATA INTEGRITY RISKS:
• Category consistency across all log tables critical for accurate reporting
• Status field validation needed (should be dropdown with Approved/Pending)
• No data validation on numeric fields (budget amounts, costs)
• Missing error handling for deleted reference data
IMPROVEMENT RECOMMENDATIONS
IMMEDIATE IMPROVEMENTS (High Priority):
1. Fix PAY_APP calculation errors - resolve #VALUE! errors
2. Repair Power Pivot connection - resolve #NAME? errors in CUBE formulas
3. Add data validation dropdowns:
• Status fields: Approved, Pending, Cancelled
• Categories: Link to zz_data cost code list
• Vendors: Link to tblVendors
FORMULA OPTIMIZATION (Medium Priority):
4. Convert complex LET formulas to named ranges or LAMBDA functions
5. Replace CUBE formulas with direct table relationships where possible
6. Implement structured references consistently across all sheets
7. Add error handling with IFERROR wrapping for critical calculations
USER EXPERIENCE ENHANCEMENTS (Lower Priority):
8. Add charts to Budget Forecast for visual budget vs. actual analysis
9. Create summary dashboard with KPI metrics
10. Implement conditional formatting for over-budget categories
11. Add print-friendly formatting and page breaks
12. Create user input forms with VBA for easier data entry
VERSION CONTROL & MAINTENANCE
• Save incremental versions when making structural changes
• Recommended naming: ProjectName_BudgetTracker_v1.0.xlsx

## 00_JobSetup
Job Setup
Property: | 40mallrd
Job Name: | 40 Mall Rd Ste 206 PreTI
Job SF: | 1328
Project Manager: | Craig Sorbello
Job Status: | IN PROGRESS
Job Type: | PRE TI
Projected Start Date: |  | Boots in ground? Permit submitted? When?
Projected Completion Date: |  | C of O?
Yardi Job Code: | dev-23
Scope of Work:
Fee/Contingency Setup
CM Fee % : |  | 007400 - Construction Management Fee
GC Fee % : |  | 007200 - GC Fee
GC Insurance % : |  | 007316 - GC Insurance
Dev Fee Type : |  | n/a
Dev Fee $ : |  | 001900 - Development Fee
Dev Fee % : |  | 001900 - Development Fee
Soft Cost Contingency % : |  | 001099 - Soft Costs - Other
Owner Contingency % : |  | 001980 - Owner Const Cost Contingency
GC Contingency % : |  | 012116 - GC Cost Contingency
Billing Setup
Client/Tenant: | n/a
Form Type: | n/a | Estimate, invoice, pay app
Invoice Date:
Invoice /AIA #:

## 01_ForecastLog
FORECAST LOG
40 Mall Rd Ste 206 PreTI
40 Mall Road
1328 |  |  |  |  | maybe remove?
Vendor | Category | Forecasted Cost Type | Forecasted Cost Amount | Forecasted Cost Status | Date Entered | Commitment Notes
3 Phase Elevator Corp. | 140010 - Elevator | Initial Estimate | 4000 | Pending
A & M Roofing & Sheet Metal Co., Inc
Boucher Acoustic LLC | 095000 - Ceilings | Subcontract | 6140 | Accepted | 2025-07-28 |  | Vendor | Category | Forecasted Cost Type | Forecasted Cost Amount | Forecasted Cost Status | Date Entered | Commitment Notes
Commercial Fire Sprinkler, Inc. | 210010 - Fire Suppression - Total | Subcontract | 3900 | Accepted | 2025-07-28
GSD Associates, LLC | 001010 - Architect Fee | Purchase Order | 4000
Lapery Painting | 099000 - Painting and Coating | Subcontract | 3940 | Accepted | 2025-07-28 |  | Vendor
Lapery Painting | 099000 - Painting and Coating | Subcontract CO #1 | 1000 | Accepted |  |  | Category
Paglia Plastering, Inc. | 092000 - Framing and Drywall | Subcontract | 10100 | Accepted | 2025-07-28 |  | Forecasted Cost Type
Precision Demolition, Inc. | 024000 - Demo - Total | Subcontract | 3100 | Accepted | 2025-07-28 |  | Forecasted Cost Amount
R&M Glass LLC | 084300 - Storefronts | Subcontract | 1806 | Accepted | 2025-07-28 |  | Forecasted Cost Status
R&M Glass LLC | 084300 - Storefronts | Subcontract CO #1 | 1806 | Accepted | 2025-07-28 | added 6 windows | Commitment Notes
Rizzo's Floor Covering | 096000 - Flooring | Subcontract | 500 | Accepted | 2025-07-28
RJK Company, Inc. | 008010 - Labor - Project Manager
Systems Electrical Services Co., Inc. | 260010 - Electrical - Total | Subcontract | 9325 | Accepted | 2025-07-28
Able Air Corp
|  | FORECAST AMOUNT: | 49617

## 04_VendorDetail
Vendor Detail
40 Mall Rd Ste 206 PreTI
40 Mall Road
1328
| Vendor Name | Subcontract | Change Orders | Purchase Orders | Total Committed | Estimated Cost | Invoiced to Date | Project Manger Notes
3 Phase Elevator Corp. | #N/A | 0 | 0 | 0 | 0 | 4000 | 0
A & M Roofing & Sheet Metal Co., Inc |  | 0 | 0 | 0 | 0 | 0 | 0
Boucher Acoustic LLC |  | 6140 | 6140 | 0 | 12280 | 6140 | 0
Commercial Fire Sprinkler, Inc. |  | 3900 | 3900 | 0 | 7800 | 3900 | 0
GSD Associates, LLC |  | 0 | 0 | 4000 | 4000 | 4000 | 0
Lapery Painting |  | 3940 | 4940 | 0 | 8880 | 4940 | 0
Paglia Plastering, Inc. |  | 10100 | 10100 | 0 | 20200 | 10100 | 0
Precision Demolition, Inc. |  | 3100 | 3100 | 0 | 6200 | 3100 | 0
R&M Glass LLC |  | 1806 | 3612 | 0 | 5418 | 3612 | 0
Rizzo's Floor Covering |  | 500 | 500 | 0 | 1000 | 500 | 0
RJK Company, Inc. |  | 0 | 0 | 0 | 0 | 0 | 0
Systems Electrical Services Co., Inc. |  | 9325 | 9325 | 0 | 18650 | 9325 | 0
Able Air Corp |  | 0 | 0 | 0 | 0 | 0 | 0
GSD Associates, LLC |  | 0 | 0 | 4000 | 4000 | 4000 | 0
[7 empty] | 0 |  | #N/A
0
0
0
|  | 38811 |  | 8000 | 88428 | 53617 | 0

## 02_BudgetLog
BUDGET LOG
40 Mall Rd Ste 206 PreTI
40 Mall Road
1328
Category | Budget Type | Budget Amount | Budget Status | Date Entered | Budget Notes
001100 - Building Permits and Fees | Original Budget | 686.63 | Approved | 2025-07-28 | Initial PM Forecast
008010 - Labor - Project Manager | Original Budget | 3700 | Approved | 2025-07-28 | Initial PM Forecast
008020 - Labor - Super | Original Budget | 2700 | Approved | 2025-07-28 | Initial PM Forecast
008030 - Labor - Foreman | Original Budget | 1440 | Approved | 2025-07-28 | Initial PM Forecast
008050 - Labor - General Labor | Original Budget | 960 | Approved | 2025-07-28 | Initial PM Forecast
010010 - General Requirements - Total | Original Budget | 1558.56 | Approved | 2025-07-28 | Initial PM Forecast
024000 - Demo - Total | Original Budget | 3100 | Approved | 2025-07-28 | Initial PM Forecast
081000 - Doors, Frames, & Hardware | Original Budget | 4500 | Approved | 2025-07-28 | Initial PM Forecast
084300 - Storefronts | Original Budget | 1806 | Approved | 2025-07-28 | Initial PM Forecast
084400 - Blinds | Original Budget | 1050 | Approved | 2025-07-28 | Initial PM Forecast
092000 - Framing and Drywall | Original Budget | 10100 | Approved | 2025-07-28 | Initial PM Forecast
095000 - Ceilings | Original Budget | 6140 | Approved | 2025-07-28 | Initial PM Forecast
096000 - Flooring | Original Budget | 500 | Approved | 2025-07-28 | Initial PM Forecast
099000 - Painting and Coating | Original Budget | 3940 | Approved | 2025-07-28 | Initial PM Forecast
210010 - Fire Suppression - Total | Original Budget | 3900 | Approved | 2025-07-28 | Initial PM Forecast
230010 - HVAC - Total | Original Budget | 2500 | Approved | 2025-07-28 | Initial PM Forecast
260010 - Electrical - Total | Original Budget | 9325 | Approved | 2025-07-28 | Initial PM Forecast
Total |  | 57906.19

## 03_BudgetReport
BUDGET REPORT
40 Mall Rd Ste 206 PreTI
40 Mall Road
1328
| (1) | (2) | (1)+(2)= (3) |  | (a) | (b) | (a)+(b)= (c) |  | (c) - (3)
Category | Original Budget | Approved Changes | Revised Budget | Revised Budget PSF | Committed Cost | Estimated Costs | Forecasted Final Cost | Forecasted Cost PSF | Forecasted (Over)/Under | Invoiced to Date | Project Manger Notes
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## zz_data
PropertyCode | PropertyName | ProjectManager | VendorCode | VendorName | Category | CostCode | Description | JobType | JobStatus | DevFeeType | ForecastType | ForecastStatus | BudgetType | BudgetStatus | Vendors_Dynamic
100_q | 100 Quannapowitt Parkway | Doug Malone | 3.phase | 3 Phase Elevator Corp. | 001010 - Architect Fee | 001010 | Architect Fee | TI | BUDGETING | n/a | Initial Estimate | Pending | Original Budget | Pending | #N/A
10columb | 10 Columbia Drive | Craig Sorbello | amconst | A & M Const Co Inc | 001015 - Landscape Architect | 001015 | Landscape Architect | PRE TI | SCHEDULED | Fixed | Revised Estimate | Accepted | Budget Adjustment | Approved
10state | 10 State Street | Michael Camire | amroofing | A & M Roofing & Sheet Metal Co., Inc | 001030 - MEP Engineering Fee | 001030 | MEP Engineering Fee | CAPEX | IN PROGRESS | Percentage | Actual Cost | Cancelled | Change Order | Rejected
111sbed | 111 South Bedford | Brendan Leahy | rose | A J Rose Carpet & Rugs | 001040 - Civil Engineering Fee | 001040 | Civil Engineering Fee | DEV | COMPLETED |  | Purchase Order
11delta | 11 Delta Drive | Andy Frey | abcsupp | ABC Supply Co., Inc. - MBA #737 | 001045 - Other Consultant Fees | 001045 | Other Consultant Fees | GC | CLOSED |  | Subcontract
11exec | 11 Executive Park |  | ableair | Able Air Corp | 001050 - Environmental Engineering Fee | 001050 | Environmental Engineering Fee |  | CANCELLED |  | Subcontract CO #1
12_exec | 12 Executive Drive |  | aic | Acadia Insurance Company | 001060 - Traffic Engineering Fee | 001060 | Traffic Engineering Fee |  |  |  | Subcontract CO #2
121tech | 121 Technology Drive |  | accurateair | Accurate Air | 001070 - Geotech Engineering Fee | 001070 | Geotech Engineering Fee |  |  |  | Subcontract CO #3
12inno | 12 Innovation |  | acmgroup | ACM Group, Inc. | 001080 - Structural Engineering Fee | 001080 | Structural Engineering Fee |  |  |  | Subcontract CO #4
12kent | 12 Kent Way |  | agj | AGJ Construction Inc. | 001090 - Legal | 001090 | Legal |  |  |  | Subcontract CO #5
13hampsh | 13 Hampshire Drive |  | airdesign | Air Design Services, Inc. | 001099 - Soft Costs - Other | 001099 | Soft Costs - Other |  |  |  | Subcontract CO #6
14celina | 14 Celina Avenue |  | amai | Allen & Major Associates, Inc. | 001100 - Building Permits and Fees | 001100 | Building Permits and Fees |  |  |  | Subcontract CO #7
153range | 153 Rangeway Road |  | alscustom | Al's Custom Tile | 001900 - Development Fee | 001900 | Development Fee |  |  |  | Subcontract CO #8
15cont | 15 Continental Boulevard |  | baysideengin | Bayside Engineering, Inc. | 001910 - Mgmt & Supervision | 001910 | Mgmt & Supervision |  |  |  | Subcontract CO #9
15guest | 15 Guest Street |  | boodryelect | Boodry Electric LLC | 001980 - Owner Const Cost Contingency | 001980 | Owner Const Cost Contingency |  |  |  | Subcontract CO #10
16celina | 16 Celina Avenue |  | bbw | Boston Building Wraps, INC | 001998 - Builders Risk | 001998 | Builders Risk
16delta | 16 Delta Drive |  | boucher | Boucher Acoustic LLC | 007200 - GC Fee | 007200 | GC Fee
17_22del | 17 & 22 Delta |  | burlingtonlu | Burlington Lumber Co. | 007316 - GC Insurance | 007316 | GC Insurance
17hampsh | 17 Hampshire Avenue |  | campbell | Campbell Co Electric LLC | 007400 - Construction Management Fee | 007400 | Construction Management Fee
18celina | 18 Celina Ave |  | carlyle | Carlyle Investment Management LLC | 008010 - Labor - Project Manager | 008010 | Labor - Project Manager
18cont | 18 Continental Boulevard |  | casella | Casella Waste Systems, Inc. | 008020 - Labor - Super | 008020 | Labor - Super
20blanch | 20 Blanchard Road |  | bostonfire | City of Boston | 008030 - Labor - Foreman | 008030 | Labor - Foreman
20cont | 20 Continental Boulevard |  | methuen.plan | City of Methuen | 008040 - Labor - Carpenter | 008040 | Labor - Carpenter
24flagst | 24 Flagstone Drive |  | codered | Code Red Consultants, LLC | 008050 - Labor - General Labor | 008050 | Labor - General Labor
290shrew | 290 Shrewsbury Street |  | cohasset | Cohasset Investment and Development LLC | 010010 - General Requirements - Total | 010010 | General Requirements - Total
326_bal | 326 Ballardvale LLC |  | cds | Commercial Drapery Systems | 012116 - GC Cost Contingency | 012116 | GC Cost Contingency
33cherry | 33 Cherry Hill Drive |  | cfsi-jason | Commercial Fire Sprinkler, Inc. | 012119 - Testing and Inspection Allow | 012119 | Testing and Inspection Allow
350gay | 350 Gay Street |  | construx | Construx Inc. | 012143 - Weather & Winter Conditions | 012143 | Weather & Winter Conditions
360_npd | 360 Narragansett Park Drive |  | core.env | Core Environmental Services, Inc. | 012663 - Change Orders | 012663 | Change Orders
368pepsi | 368 Pepsi Road |  | cw | Cushman & Wakefield | 013590 - GC Mgmt & Supervision | 013590 | GC Mgmt & Supervision
405_coch | 405 Cochituate Road LLC |  | dacon | Dacon Corporation | 014126 - Permit Requirements | 014126 | Permit Requirements
40mallrd | 40 Mall Road |  | reliantjanit | DCS Service Inc. dba Reliant Janitorial Service, LLC | 017423 - Cleaning | 017423 | Cleaning
40warren | 40 Warren Owner LLC |  | digitalanalo | Digital Analog Control Systems | 022100 - Surveys | 022100 | Surveys
44indus | 44 Industrial |  | dsinorth | DSI North Door Systems, Inc. | 024000 - Demo - Total | 024000 | Demo - Total
44mallrd | 44 Mall Road |  | elhs | E.L. Harvey & Sons, Inc. | 025000 - Site Remediation | 025000 | Site Remediation
486amher | 486 Amherst Street |  | eastcoastmet | East Coast MetalWorks Inc | 028010 - Facility Remediation - Total | 028010 | Facility Remediation - Total
4townsen | 4 Townsend West |  | eastcoast | East Coast Wrecking Incorporated | 028200 - Asbestos Remediation | 028200 | Asbestos Remediation
501_grif | 501 Griffin Brook Drive |  | eaton | Eaton Horticultural Landscape | 028500 - Mold Remediation | 028500 | Mold Remediation
50mallrd | 50 Mall Road |  | miikaebbrell | Ebbrell Architecture & Design | 030010 - Concrete - Total | 030010 | Concrete - Total
542amher | 542 Amherst Street |  | ebi | EBI Consulting | 040010 - Masonry - Total | 040010 | Masonry - Total
54mallrd | 54 Mall Road |  | esei | Electrical Systems Engineering, Inc. | 050010 - Metals - Total | 050010 | Metals - Total
55cambr | 55 Cambridge Street |  | edei | Environmental Design Engineering Inc. | 052000 - Structural Steel | 052000 | Structural Steel
55north | 55 Northeastern Blvd |  | fsp | Farfaras & Son Plumbing & Heating Co, In | 055100 - Stairs | 055100 | Stairs
5flagst | 5 Flagstone Drive |  | msc | FBM - Farmingdale | 060010 - Carpentry - Total | 060010 | Carpentry - Total
600gbd | 600 Griffin Brook Drive |  | harryfeldman | Feldman Geospatial | 061000 - Rough Carpentry | 061000 | Rough Carpentry
60mallrd | 60 Mall Road |  | fgd | Fimbel Paunet Corp. dba Fimbel Garage Doors | 070010 - Thermal and Moisture Protection | 070010 | Thermal and Moisture Protection - LUMP SUM
72cherry | 72 Cherry Hill Drive |  | megafood | FoodState, Inc dba MegaFood | 071000 - Dampproofing and waterproofing | 071000 | Dampproofing and waterproofing
77sbnew | 77 South Bedford |  | goveenvironm | Gove Environmental Services, Inc | 072500 - Exterior Finishes | 072500 | Exterior Finishes
805mid | 805 Middlesex Tpke |  | giw | Grainger | 074000 - Roofing and Siding Panels | 074000 | Roofing and Siding Panels
85nwblvd | 85 Northwest Boulevard |  | gpi | Greenman-Pedersen, Inc. | 075000 - Roofing - Total | 075000 | Roofing - Total
8tech | 8 Tech LLC |  | gsd | GSD Associates, LLC | 080010 - Openings - Total | 080010 | Openings - Total
99sbed | 99 South Bedford Street |  | halcon | Halcon Carpentry Inc | 081000 - Doors, Frames, & Hardware | 081000 | Doors, Frames, & Hardware
9hampsh | 9 Hampshire Dr |  | hannon | Hannon Electric, Inc. | 083323 - Overhead Ceiling Doors | 083323 | Overhead Ceiling Doors
aviation | Aviation Way Owner(Yogibo |  | haynerswanso | Hayner/Swanson, Inc. | 084300 - Storefronts | 084300 | Storefronts
charlest | SUS of Charlestown |  | hightech | High-Tech Electrical Contractors, Inc. | 084400 - Blinds | 084400 | Blinds
loomis | 5 Aviation Investors LLC |  | hub.building | Hub Building & Maintenance Inc. | 085000 - Windows | 085000 | Windows
mallr10 | 10 Mall Road |  | jmservice | J M Service Co LLC | 088100 - Glass Glazing | 088100 | Glass Glazing
mallr20 | 20 Mall Road |  | jbnb | JBNB Construction LLC | 092000 - Framing and Drywall | 092000 | Framing and Drywall
plymouth | Natalie Way Owner LLC |  | jensenhughes | Jensen Hughes, Inc. | 093000 - Tiling | 093000 | Tiling
quarrysq | Quarry Square |  | jod | Jodi General Contractor | 095000 - Ceilings | 095000 | Ceilings
rjkcoinc | RJK Company, Inc. |  | kaloutas | Kaloutas & Company Inc. | 095100 - Acoustical Ceilings | 095100 | Acoustical Ceilings
101stat | 101 Station Landing |  | kam | Kamco Supply Corp. of Boston | 096000 - Flooring | 096000 | Flooring
|  |  | kannanpricon | Kannan & Pricone Plumbing & Heating Inc | 096119 - Concrete Floor Staining | 096119 | Concrete Floor Staining
|  |  | kjm | KJ Miller Mechanical | 096800 - Carpeting | 096800 | Carpeting
|  |  | lapery | Lapery Painting | 099000 - Painting and Coating | 099000 | Painting and Coating
|  |  | lk | Locks & Keys, Inc | 100010 - Specialties - Total | 100010 | Specialties - Total
|  |  | lumens | Lumens | 100151 - Parking Lot | 100151 | Parking Lot
|  |  | mci | Mass Cabinets Inc. | 100191 - Building Exterior - Facade | 100191 | Building Exterior - Facade
|  |  | mcservices | MC Services, LLC | 105000 - Storage Specialties | 105000 | Storage Specialties
|  |  | mccarthyson | McCarthy & Son Landscaping, Inc | 100561 - Millwork | 100561 | Millwork
|  |  | mcp | McSweeney Painting Co. | 101400 - Signage | 101400 | Signage
|  |  | mdw | MD Weaver Corporation | 102200 - Partitions | 102200 | Partitions
|  |  | metal | Metalcraft Door Co., Inc. | 107313 - Awnings | 107313 | Awnings
|  |  | camire.micha | Michael Camire | 110010 - Equipment - Total | 110010 | Equipment - Total
|  |  | nesp | NewEngland SurfacePreparation | 111000 - Vehicle and Pedestrian Equip | 111000 | Vehicle and Pedestrian Equip
|  |  | ncc | North Crescent Condominium c/o SBC2, LLC | 113001 - Utilities | 113001 | Utilities
|  |  | northeastgeo | Northeast Geotechnical, Inc. | 113501 - Trash Removal | 113501 | Trash Removal
|  |  | onyx | Onyx Creative, Inc. | 120010 - Furnishings and Equip - Total | 120010 | Furnishings and Equip - Total
|  |  | outdoor | Outdoor Pride Landscaping, LLC | 122000 - Window Treatments | 122000 | Window Treatments
|  |  | paglia | Paglia Plastering, Inc. | 130000 - Special Construction | 130000 | Special Construction
|  |  | patskey | Pats Key N Lock, Inc. | 140010 - Elevator | 140010 | Elevator
|  |  | pavements | Pavements, Inc. | 210010 - Fire Suppression - Total | 210010 | Fire Suppression - Total
|  |  | prec.demo | Precision Demolition, Inc. | 212000 - Fire-Extinguishing Systems | 212000 | Fire-Extinguishing Systems
|  |  | pfe | Precision Fitness Equipment | 220010 - Plumbing - Total | 220010 | Plumbing - Total
|  |  | rmglass | R&M Glass LLC | 230010 - HVAC - Total | 230010 | HVAC - Total
|  |  | rhp | R.H. Partition Co. | 260010 - Electrical - Total | 260010 | Electrical - Total
|  |  | rjkcoinc | R.J. Kelly Co., Inc. | 280010 - Fire Alarm | 280010 | Fire Alarm
|  |  | radner | Radner Design Associates, Inc | 282000 - Electronic Access and Security | 282000 | Electronic Access and Security
|  |  | rizzo | Rizzo's Floor Covering | 283000 - Electronic Detection and Alarm | 283000 | Electronic Detection and Alarm
|  |  | roofmainten | Roof Maintenance & Systems, Inc. | 310010 - Sitework - Total | 310010 | Sitework - Total
|  |  | rooflifters | Rooflifters USA LLC | 321700 - Paving | 321700 | Paving
|  |  | safetyenviro | Safety Environmental Consultants | 323100 - Fences and Gates | 323100 | Fences and Gates
|  |  | saulewing | Saul Ewing LLP | 327000 - Wetlands | 327000 | Wetlands
|  |  | scotland | Scotland Bridge Woodworking | 329000 - Landscaping | 329000 | Landscaping
|  |  | servmaster | ServiceMaster Restore
|  |  | sgt | Sonnys Glass Tinting LLC
|  |  | spark | Spark Electrician Services LLC
|  |  | sec | Stanley Elevator Co., Inc.
|  |  | steelblue | Steelblue Building Components LLC
|  |  | stellos | Stellos Electric Supply Inc.
|  |  | stalarm | Steven D. Tanner
|  |  | ssi | Structural Systems, Inc.
|  |  | sr | Sunbelt Rentals
|  |  | sesci | Systems Electrical Services Co., Inc.
|  |  | gran.place | The Granite Place
|  |  | mcg | The Morin-Cameron Group, Inc.
|  |  | throne | The Throne Depot
|  |  | durham | Town of Durham, NH
|  |  | wakefield | Town of Wakefield
|  |  | tucksland | Tucks Land Care Inc
|  |  | uts_ma | U.T.S of Massachusetts, Inc.
|  |  | uline | Uline
|  |  | usadem | USA Demolition, Inc.
|  |  | vlavoie | V. Lavoie Contracting, LLC
|  |  | verizon-rpc | Verizon - RPC
|  |  | vpsa | View Point Sign and Awning
|  |  | vmi | VMI Cleaning Corp.
|  |  | gc | W. J. Grosvenor & Co.
|  |  | wayne | Wayne's Drains
|  |  | whitecap | White Cap, L.P.
|  |  | yates | Yates Electric Service Inc.
|  |  | rjkcoinc | RJK Company, Inc.
|  |  | n/a | n/a - estimate only

## ErrorLog (hidden)
Timestamp | Error # | Description | Procedure | Object Context | Line #
2025-06-22 21:34 | 91 | Object variable or With block variable not set | LogError | Data validation on 'tblCommitments' | 8140
2025-06-22 21:34 | 91 | Object variable or With block variable not set | LogError | Data validation on 'tblChangeOrders' | 9140
2025-06-22 21:34 | 91 | Object variable or With block variable not set | LogError | Setting formulas in 'tblBudget' | 7160

## zzz_yardi import
Grey shaded cells should not be edited to successfully import
Job Detail Id | Category | Description | Budget | Revision | Remarks
4124 | 001010 | Architect Fee | 0 | 0
4209 | 001030 | MEP Engineering Fee | 0 | 0
4171 | 001100 | Building Permits and Fees | 0 | 0
4386 | 007200 | GC Fee | 0 | 0
4387 | 007316 | GC Insurance | 0 | 0
4385 | 007400 | Construction Management Fee | 0 | 0
4105 | 008010 | Labor - Project Manager | 0 | 0
4939 | 008020 | Labor - Super | 0 | 0
4360 | 008040 | Labor - Carpenter | 0 | 0
4656 | 008050 | Labor - General Labor | 0 | 0
4420 | 010010 | General Requirements - Total | 0 | 0
4587 | 014126 | Permit Requirements | 0 | 0
4660 | 024000 | Demo - Total | 0 | 0
4439 | 075000 | Roofing - Total | 0 | 0
4712 | 081000 | Doors, Frames, & Hardware | 0 | 0
4672 | 083323 | Overhead Ceiling Doors | 0 | 0
4735 | 092000 | Framing and Drywall | 0 | 0
4745 | 096000 | Flooring | 0 | 0
4711 | 099000 | Painting and Coating | 0 | 0
4412 | 210010 | Fire Suppression - Total | 0 | 0
4532 | 220010 | Plumbing - Total | 0 | 0
4277 | 230010 | HVAC - Total | 0 | 0
4533 | 260010 | Electrical - Total | 0 | 0
4916 | 310010 | Sitework - Total | 0 | 0

## TENANT_ESTIMATE
ESTIMATE
|  | Date | Estimate Prepared By
55 Cambridge Street - Suite 300
Burlington, MA 01803
(781)-272-2899
Project: | Lobby-Bldg Upgrade
Location: | 60 Mall Rd
Client:
Client Contact:
Description of Work:
Total Cost |  |  | 935092.12
* Price includes any Taxes, Materials, Labor, and Fees. * Payment is due 50% upon Estimate execution, and the balance upon completion of the Estimated Work. * All work to be performed during normal business hours unless otherwise noted. * Pricing is good for 30 days.
All material is guaranteed to be as specified. All work to be completed and supervised by the R.J. Kelly Co., Inc. in accordance with specifications submitted in this estimate. Any alteration or deviation from above specifications involving additional extra costs will be executed only upon additional written change orders and will become an additional extra on the project. Tenant will be responsible for the costs associated with any changes to original project. In the event of any material or intent discretion between the Lease Agreement and any subsequently produced construction documents the Lease Agreement shall apply unless specifically outlined and noted as a "specific scope change" within an accepted change order between RJK Co and Tenant or authorized representative.
Estimate Acceptance By:
______________________________________________________________ |  |  | ____________________
Tenant Representative |  |  | Date

## PAY_APP
|  |  |  | RJ Kelly Co., Inc. |  | For: | 121 Tech Owner LLC |  |  | App. No. | 5 |  |  | RJ Kelly Co., Inc. |  | For: | 121 Tech Owner LLC |  |  | App. No. | 5
|  |  |  | 55 Cambridge Street |  |  | 55 Cambridge Street |  |  | Date: | 2025-08-03 |  |  | 55 Cambridge Street |  |  | 55 Cambridge Street |  |  | Date: | 2025-08-03
|  |  |  | Burlington, MA 01803 |  |  | Burlington, MA 01803 |  |  | Period Start: | 2023-11-01 |  |  | Burlington, MA 01803 |  |  | Burlington, MA 01803 |  |  | Period Start: | 2023-11-01
|  |  |  | p: (781) 272-2899 |  | Project: | Brazonics GC |  |  | Period End: | 2023-12-31 |  |  | p: (781) 272-2899 |  | Project: | Brazonics GC |  |  | Period End: | 2023-12-31
[18 empty] | Brazonics.GC | Brazonics.GC
Contractor's Application for Payment | [11 empty] | Work Summary
[12 empty] | Cost Code | Description |  |  | Scheduled Value | Previous | Current | Total | % Complete | Balance to Complete | 5% Retainage
Change Order Summary |  |  | Additions |  | Deductions |  |  | Original Contract Sum |  |  | 9374183.45
Total Approved in Prior Months | [7 empty] | Net Change by Change Order |  |  | 0 | 010010 | General Requirements |  |  | 92409.5 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | #VALUE! | Total Completed Check to Inv Log
Total Approved this Month | [7 empty] | Contract Sum to Date |  |  | 9374183.45 | 024000 | Demo |  |  | 261545 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0
|  | TOTALS | 0 |  | 0 |  |  | Total Completed and Stored |  |  | #VALUE! | 030010 | Concrete |  |  | 374142.2 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0
Owner's Contingency Assignment |  |  | 0 |  | 0 |  |  | 5% | Retainage to Date |  | 0 | 052000 | Misc. Metals & Structural Steel |  |  | 149550 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0
[8 empty] | Total Earned Less Retainage |  |  | #VALUE! | 100561 | Millwork & Solid Surfaces |  |  | 29333 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0
Total Changes to Contract Sum |  |  | 0 |  | 0 |  |  | Previous Certificates for Payment |  |  | #VALUE! | 075000 | Roofing |  |  | 62500 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0
[8 empty] | Current Payment Due |  |  | #VALUE! | 081000 | Doors, Frames, & Hardware |  |  | 116266.4 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0
[8 empty] | Balance to Finish, plus Retainage |  |  | #VALUE! | 083323 | Overhead Doors |  |  | 138177.68 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0
[12 empty] | 088100 | Glass Glazing |  |  | 40697.41 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0
| Contractor's Sworn Statement and Affidavit | [5 empty] | Current Payment Due |  |  |  |  | 092000 | Framing & Drywall |  |  | 802775 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0
| RJ Kelly Co. Inc affirms to the best of our knowledge and understanding that the Work included in this Application for Payment has been completed approximately to the level of progress indicated and to the detail outlined in the Contract Documents, that all amounts have been paid by RJ Kelly Co. Inc to its first-tier subcontrators as listed, and RJ Kelly Co. Inc is due the amount shown as Current Payment Due. | [5 empty] | #VALUE! |  |  |  |  | 095000 | Ceilings |  |  | 168150 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0
[12 empty] | 096000 | Flooring |  |  | 115271.04 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0
[12 empty] | 099000 | Painting |  |  | 147165 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0
[7 empty] | Amount Authorized for Payment by Owner |  |  |  |  | 130000 | Specialties - Bathrooms |  |  | 42347.84 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 |  | 125
[7 empty] | #VALUE! |  |  |  |  | 110010 | Equipment |  |  | 114014.5 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 |  | 105
[12 empty] | 210010 | Fire Suppression |  |  | 287800 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 |  | 80
[12 empty] | 220010 | Plumbing |  |  | 324600 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 |  | 90
| By: | [5 empty] | By: |  |  |  |  | 230010 | HVAC & Controls |  |  | 1547000 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 |  | 62.5
[12 empty] | 260010 | Electrical & Fire Alarm |  |  | 1854407 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0
[12 empty] | 329000 | Sitework & Fencing |  |  | 198912 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0
| Doug Malone, VP of Construction, RJ Kelly Co., Inc. | [5 empty] | Owner or Owner's Authorized Representative | [5 empty] | Subtotal - Contractor Hard Costs |  |  | 6867063.57 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0
[12 empty] | LABOR | GC Mgmt & Labor |  |  | 848280 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[12 empty] | 007200 | GC Fee & Overhead | 5% |  | 442178.46 | 43495.73 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[12 empty] | 007316 | GC Insurance | 2% |  | 176871.39 | 9651.67 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[12 empty] | 012116 | GC Contingency |  |  | 695765.23 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[12 empty] | 001010 | Architectual & Engineering |  |  | 287168 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[12 empty] | 001100 | Building Permit |  |  | 56856.8 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[11 empty] | ` |  | Subtotal - Contractor Soft Costs |  |  | 2507119.88 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0
[13 empty] | Total - Contract |  |  | 9374183.45 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0
[15 empty] | GC Overhead | 587612.58
[15 empty] | GC Fee Difference | 0 | 499176.88 | Remaining Budget
[15 empty] | GC Insurance Difference | -88435.7
[16 empty] | 9374183.45 | Confirm amount that has been disclosed?
[16 empty] | 0 | Remaining Budget