## DRIVER
GENERAL - INTERNAL: |  | Notes
Property: | PROPERTY A
Tenant Name: | TENANT X
Unit #: | n/a
SF: | 75000
Improvement Allowance Amount: | 750000 | FROM TENANT IMPROVEMENTS AGREEMENT
Other Allowance Amount: |  | FROM TENANT IMPROVEMENTS AGREEMENT/OTHER
Supervisory Fee: | 1% | FROM TENANT IMPROVEMENTS AGREEMENT
Supervisory Fee Cap:
Supervisory Fee Pool: | IMPROVEMENTS | 1% on total costs of Tenant Improvement or amount of Allowance
Retainage: | 5% | FROM TENANT IMPROVEMENTS AGREEMENT
Uniform Improvement Clause: |  | Yes/No
Funding Structure: | Pari passu | (i.e. LL $ first, Tenant $ first, pari passu) - should maybe make drop down
DEADLINSE & APPROVALS |  | Notes
Space Plan Deadline:
Plans and Specs Deadline:
LL Approved Tenant's Architect:
LL Approved Tenant Contractor:
EXCLUDED USES
FROM TENANT IMPROVEMENTS AGREEMENT
APPROVED COSTS:
FROM TENANT IMPROVEMENTS AGREEMENT
TENANT WORK INFO: |  | Notes
Total Original Project Buget: | 905000 | FROM TENANT PROJECT BUDGET, consistent with Plans & Specs
Approved LL Change Orders: | #REF! | FROM TENANT, "Changes to Plans & Specs:
Total Current Project Budget: | 905000 | Original + Approved Change Orders
TENANT CONTACTS:
NAME | COMPANY | POSITION | EMAIL | PHONE #

## TIA TRACKER (hidden)
GENERAL:
Property: | PROPERTY A
Tenant Name: | TENANT X
Unit #: | n/a
SF: | 75000
FUNDING INFO
NOTES:
Total TIA Amount: | 750000
less: Supervisory Fee: | -9050
740950
less: Retainage: | -37047.5
Total Release Pre-Retainage: | 703902.5
Total Retainage Held: | 37047.5
TENANT ALLOWANCE REQUESTS
REQUEST # | REQUEST DATE | TOTAL | SUPERVISORY | RETAINAGE | NET | RUNNING NET | PAYMENTS | NOTES:
REQUEST #1 | [5 empty] | 0 | 0
REQUEST #2 | [5 empty] | 0 | 0
REQUEST #3 | [5 empty] | 0 | 0
REQUEST #4 | [5 empty] | 0 | 0
REQUEST #5 | [5 empty] | 0 | 0
REQUEST #6 | [5 empty] | 0 | 0
REQUEST #7 | [5 empty] | 0 | 0
REQUEST #8 | [5 empty] | 0 | 0
REQUEST #9 | [5 empty] | 0 | 0
REQUEST #10 | [5 empty] | 0 | 0
TOTAL |  | 0 | 0 | 0 | 0
DISBURSEMENTS
REQUEST # | TOTAL | PAYMENT DATE
TOTAL | 0

## BUDGET & TRACKER
| RJ Kelly Co., Inc. | Property: | PROPERTY A
| 55 Cambridge Street | Tenant: | TENANT X
| Burlington, MA 01803 | SF: | 75000
| p: (781) 272-2899 | Funding: | Pari passu
[6 empty] | REQUEST DATE: | 0 | 0 | 0 | 0
| DESCRIPTION |  | ORIGINAL BUDGET | APPROVED CHANGES | CURRENT BUDGET |  | REQUEST #1 | REQUEST #2 | REQUEST #3 | REQUEST #4 | REQUEST #5 | REQUEST #6 | REQUEST #7 | REQUEST #8 | REQUEST #9 | REQUEST #10 | COSTS TO DATE | REMAINING BUDGET
A&E, SOFT COSTS | Architectual & Engineering |  | 15000 |  | 15000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
| Building Permit & Fees |  | 10000 |  | 10000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
| Legal & Admin |  | 7500 |  | 7500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500
| Construction Manager |  | 20000 |  | 20000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A&E, SOFT COSTS TOTAL |  |  | 52500 | 0 | 52500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 52500
GC, HARD COSTS | GC Contract Costs |  | 725000 |  | 725000 |  | 40000 | 40000 | 40000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 420000 | 305000
| Tenant-Managed Direct Costs |  | 85000 |  | 85000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85000
| FF&E / Personal Property |  | 32500 |  | 32500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32500
| Allowance for Miscellaneous Costs |  | 10000 |  | 10000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
| Project Contingency |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GC, HARD COSTS TOTAL |  |  | 852500 | 0 | 852500 |  | 40000 | 40000 | 40000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 420000 | 432500
TOTAL HARD + SOFT COSTS |  |  | 905000 | 0 | 905000 |  | 40000 | 40000 | 40000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 420000 | 485000 |  | 155000 | IMPROVEMENT ALLOWANCE EXCESS
[5 empty] | TIA AMOUNT |  | REQUEST #1 | REQUEST #2 | REQUEST #3 | REQUEST #4 | REQUEST #5 | REQUEST #6 | REQUEST #7 | REQUEST #8 | REQUEST #9 | REQUEST #10 | REQUESTED TO DATE | REMAINING ALLOWANCE | RETAINAGE RELEASE
|  |  |  | Gross Total | 750000 |  | 33149.1713 | 33149.1713 | 33149.1713 | 248618.7845 | 0 | 0 | 0 | 0 | 0 | 0 | 348066.2983 | 401933.7017 | n/a
|  | 1% |  | less: LL Supervisory Fee | -9050 |  | -331.4917 | -331.4917 | -331.4917 | -2486.1878 | 0 | 0 | 0 | 0 | 0 | 0 | -3480.663 | -5569.337 | n/a
|  | 5% |  | less: LL Project Retainage* | -37047.5 |  | -1657.4586 | -1657.4586 | -1657.4586 | -12430.9392 | 0 | 0 | 0 | 0 | 0 | 0 | -17403.3149 | -19644.1851 | 37047.5
|  |  |  | TOTAL DISBURSEMENTS | 703902.5 |  | 31160.221 | 31160.221 | 31160.221 | 233701.6575 | 0 | 0 | 0 | 0 | 0 | 0 | 327182.3204 | 376720.1796 | 37047.5
TRUE

## INVOICES
[6 empty] | 420000 | TOTAL AMOUNT
TRUE
REQUEST # | REQUEST DATE | VENDOR | BUDGET CATEGORY | INVOICE # | INVOICE DATE | AMOUNT | NOTES
REQUEST #1 |  |  | GC Contract Costs |  |  | 40000
REQUEST #2 |  |  | GC Contract Costs |  |  | 40000
REQUEST #3 |  |  | GC Contract Costs |  |  | 40000
REQUEST #4 |  |  | GC Contract Costs |  |  | 300000
REQUEST #1
REQUEST #1
REQUEST #1
REQUEST #1
REQUEST #1
REQUEST #1
REQUEST #1
REQUEST #1
REQUEST #1
REQUEST #1
REQUEST #1
REQUEST #1
REQUEST #1
REQUEST #1
REQUEST #1
REQUEST #1
REQUEST #1
REQUEST #1
REQUEST #1
REQUEST #1
REQUEST #1
REQUEST #1
REQUEST #2
REQUEST #2
REQUEST #2
REQUEST #2
REQUEST #2
REQUEST #2
REQUEST #2
REQUEST #2
REQUEST #2
REQUEST #2
REQUEST #2
REQUEST #2
REQUEST #2
REQUEST #2
REQUEST #2
REQUEST #2
REQUEST #2
REQUEST #2
REQUEST #2
REQUEST #2
REQUEST #2
REQUEST #2
REQUEST #2
REQUEST #2
REQUEST #2
REQUEST #2

## DROPDOWNS (hidden)
Yes/No | PROPERTY | REQUEST # | BUDGET CATEGORIES | CO STATUS | SUPERVISORY FEE POOL | FUNDING STRUCTURE
Yes | PROPERTY A | REQUEST #1 | Architectual & Engineering | REQUESTED | ALLOWANCE | Pari passu
No | 16 Delta Drive - (16delta) | REQUEST #2 | Building Permit & Fees | APPROVED | IMPROVEMENTS | Tenant $ First
N/A | 33 Cherry Hill Drive - (33cherry) | REQUEST #3 | Legal & Admin
| 35 Cherry Hill Drive - (35cherry) | REQUEST #4 | Construction Manager
| 368 Pepsi Road - (368pepsi) | REQUEST #5 | GC Contract Costs
| 37 Cherry Hill Road - (37cherry) | REQUEST #6 | Tenant-Managed Direct Costs
| 10 Columbia Drive - (10columb) | REQUEST #7 | FF&E / Personal Property
| 10 Mall Road - (mallr10) | REQUEST #8 | Allowance for Miscellaneous Costs
| 10 State Street - (10state) | REQUEST #9 | Project Contingency
| 100 Quannapowitt Parkway - (100_q) | REQUEST #10
11 Delta Drive - (11delta)
11 Executive Park - (11exec)
111 South Bedford - (111sbed)
12 Executive Drive - (12_exec)
12 Innovation - (12inno)
12 Kent Way - (12kent)
121 Technology Drive - (121tech)
125 Goddard Memorial Drive - (125_god)
13 Hampshire Drive - (13hampsh)
14 Celina Avenue - (14celina)
15 Continental Boulevard - (15cont)
15 Guest Street - (15guest)
153 Rangeway Road - (153range)
16 Celina Avenue - (16celina)
17 Hampshire Avenue - (17hampsh)
18 Celina Ave - (18celina)
18 Continental Boulevard - (18cont)
18 Hampshire Rd - (18hampsh)
20 Blanchard Road - (20blanch)
20 Continental Boulevard - (20cont)
20 Mall Road - (mallr20)
24 Flagstone Drive - (24flagst)
326 Ballardvale LLC - (326_bal)
327 Ruby Road - (327ruby)
350 Gay Street - (350gay)
36 Precision Drive - (36precis)
360 Narragansett Park Drive - (360_npd)
4 Townsend West - (4townsen)
40 Mall Road - (40mallrd)
405 Cochituate Road LLC - (405_coch)
44 Industrial - (44indus)
44 Mall Road - (44mallrd)
486 Amherst Street - (486amher)
5 Aviation Investors LLC - (loomis)
5 Flagstone Drive - (5flagst)
50 Mall Road - (50mallrd)
501 Griffin Brook Drive - (501_grif)
54 Mall Road - (54mallrd)
542 Amherst Street - (542amher)
55 Cambridge Street - (55cambr)
55 Northeastern Blvd - (55north)
6 Post Road - (6postrd)
6 Wentworth Drive - (6wentwth)
60 Mall Road - (60mallrd)
66 Cherry Hill Drive - (66cherry)
71 Cherry Hill Drive - (tsc71chd)
77 South Bedford - (77sbnew)
8 Blanchard - (8blanch)
8 Tech LLC - (8tech)
805 Middlesex Tpke - (805mid)
85 Northwest Boulevard - (85nwblvd)
9 Hampshire Dr - (9hampsh)
99 South Bedford Street - (99sbed)
Aviation Way Owner(Yogibo) - (aviation)
Quarry Square - (quarrysq)

## GPT cache (hidden)
{"hash":"cdc251c4361a0f65d4c1438af9f477d52ffa6111aec7f6b2ad254f09ef5212c0","version":1,"value":"[[\"The formula calculates a value based on two scenarios:\\nIf cell C16 in the DRIVER sheet equals \\\"IMPROVEMENTS\\\", it calculates 1% of the sum of F54 and F18.\\nOtherwise, it returns the lesser of: 1% of the sum of F54 and F18, or the product of cells C13 and C15 from the DRIVER sheet.\"]]"}
{"hash":"4cd55fdadc5ca345e2068cee9f320cf2177d3d26c8bacf8a65ee6ed946eb26c3","version":1,"value":"[[\"=IF(DRIVER!$C$20=\\\"Pari passu\\\",(W57/H57)*T57,IF(DRIVER!$C$20=\\\"Tenant $ First\\\",T57-(H57-W57),T57))\"]]"}
{"hash":"ae797024413f2117d65ceebafcb8e3988113938fafac60c9369ed1310c12f6b2","version":1,"value":"[[\"The formula calculates a share of income based on three possible distribution methods:\\n\\n1. If \\\"Pari passu\\\": Calculates proportional share (H36/H31 ratio multiplied by J31)\\n2. If \\\"Tenant $ First\\\": Takes tenant's share first, then any remainder up to J31\\n3. Otherwise: Returns full amount in J31\"]]"}
{"hash":"6d79715bb8564895bd081f78ea7f53b50fa317bb9b76c43dbf62543f0e27dad6","version":1,"value":"[[\"=IF(OR(J31<0,K31<0),0,IF(SUM(J31:K31)=0,0,K31/SUM(J31:K31)*J36))\"]]"}
{"hash":"988c268a96024947779f9c22b5d2aad031b76873cdad5b8d90e8944cb33bb57c","version":1,"value":"[[\"=IF(AND(K31>0,K36>0),K36/K31,\\\"\\\")\"]]"}